## Project Planner
Project Planner | Period 1 Refers to 1 April 2022
Select a period to highlight at right. A legend describing the charting follows. |  |  |  | 1 |  |  | Actual
ACTIVITY | Responsible | ACTUAL START | ACTUAL DURATION | PERIODS
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7
Full-stack: Flash error messages | Domica | 3 | 2
Front-end: Edit Profile Page | Pierson | 1 | 2
Front-end: User Profile | Pierson | 1 | 2
Back-end: Comment for events | Ethan | 1 | 2
Back-end: Event details page | Philip | 1 | 2
Front-end: Event details page | Ethan & Philip | 1 | 2
Stock Pictures for Category | Ethan | 3 | 2
Back-end: Admin User Functions | Domica | 3 | 2
Front-end: Homepage | Bryan | 1 | 2
Front-end: User Authentication | Pierson | 1 | 2
Back-end: Search/ sort events | Philip | 1 | 2
Front-end: User creation pt 2 (see more in Trello) | Pierson | 1 | 2
Front-end: View all events page | Philip | 1 | 2
Front-end: User rating | Pierson | 1 | 2
Front-end: Feeds | Bryan | 1 | 2
Back-end: Feeds | Bryan | 1 | 2
Back-end: Participate in an event, receive reminder | Ethan | 1 | 2
Back-end: Upload user profile pic and event pic | Ethan | 1 | 2
Front-end: Render user profile pic in user profile | Pierson | 3 | 2
Front-end: Render event pic in event details page | Philip | 3 | 2
For production: Redirect all console.log to output file |  | 3 | 2
Reinitialize database to update all fields | Domica | 3 | 2
Remove console.log email body in auth.controller.js | Domica | 3 | 2
Recheck all functions and clear everything for production | All | 3 | 2